## Projectplanner
Programmeplanner
[5 empty] | Period | 26 |  |  | Duration plan | [6 empty] | Actual start date | [8 empty] | % complete |  |  |  |  | Actual (outside planning) | [9 empty] | % Complete (outside planning)
Activity | Start of activitiy | Duration | Actual start date | Actual duration | Percentage complete | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160
Programme formulation | 1 | 6 | 1 | 9 | 100%
- Benefit identification | 1 | 4 | 1 | 5 | 100%
- Programme brief development | 5 | 1 | 6 | 2 | 100%
- Define governance structure | 5 | 1 | 6 | 2 | 100%
Programme preparation | 6 | 21 | 7 | 20 | 100%
- Set up team | 6 | 3 | 7 | 2 | 100%
- Analyse stakeholders | 7 | 4 | 8 | 4 | 100%
- Elaborate benefits | 12 | 5 | 12 | 5 | 100%
- Identify projects to realise benefits | 15 | 3 | 15 | 3 | 100%
- Develop programme plan | 15 | 4 | 15 | 4 | 100%
- Set up programme management instruments and structure | 16 | 2 | 16 | 2 | 100%
Programme implementation | 18 | 150 | 18 |  | 10%
Project: A social marketing project | 19 | 58 | 19 |  | 10%
- Develop project | 19 | 2 | 19 | 2 | 100%
- Commission project | 20 | 52 | 20 |  | 4%
- Close project | 72 | 2 |  |  | 0%
Project: Virtual consultation package implemented | 25 | 33 | 25 |  | 0%
- Develop project | 25 | 1 | 25 | 1 | 100%
- Commission project | 26 | 30 | 26 |  | 0%
- Close project | 56 | 2 |  |  | 0%
Project: Incentive package for staff not to use their car | 23 | 3 | 20 |  | 5%
- Develop project | 20 | 2 | 20 | 2 | 100%
- Commission project | 23 | 52 |  |  | 0%
- Close project | 75 | 3 |  |  | 0%
Project: Overview of improvements that can be made to the pharmaceuticals distribution process | 45 | 59 |  |  | 0%
- Develop project | 45 | 4 |  |  | 0%
- Commission project | 50 | 52 |  |  | 0%
- Close project | 102 | 3 |  |  | 0%
Project: Materials to encourage patients to return unused drugs | 20 | 37 | 20 |  | 10%
- Develop project | 20 | 1 | 20 | 2 | 100%
- Commission project | 21 | 35 | 22 |  | 5%
- Close project | 56 | 1 |  |  | 0%
Project: No non-recycble food wrappings in the hospital | 90 | 36 |  |  | 0%
- Develop project | 90 | 4 |  |  | 0%
- Commission project | 95 | 30 |  |  | 0%
- Close project | 125 | 2 |  |  | 0%
Project: Overview of measures that staff think can help reduce or reuse materials | 19 | 148 | 19 |  | 3%
- Develop project | 19 | 5 | 19 | 6 | 100%
- Commission project | 24 | 140 | 25 |  | 0%
- Close project | 164 | 3 |  |  | 0%
Project: Transfer from a plated system to a bulk food system. | 25 | 108 | 25 |  | 5%
- Develop project | 25 | 5 | 25 |  | 50%
- Commission project | 30 | 100 |  |  | 0%
- Close project | 130 | 3 |  |  | 0%
Project: Patients receive food in cummunal setting or undisturbed | 25 | 25 | 25 |  | 10%
- Develop project | 25 | 3 | 25 |  | 75%
- Commission project | 28 | 20 |  |  | 0%
- Close project | 48 | 2 |  |  | 0%
Project: A continuous process of monitoring of water leak detection | 20 | 25 | 20 |  | 10%
- Develop project | 20 | 3 | 20 | 3 | 100%
- Commission project | 23 | 20 | 23 |  | 20%
- Close project | 43 | 2 |  |  | 0%
Project: Overview of areas were savings can be made through small technical interventions | 23 | 26 | 23 |  | 10%
- Develop project | 23 | 3 | 23 | 3 | 100%
- Commission project | 23 | 20 |  |  | 0%
- Close project | 43 | 3 |  |  | 0%
Project: Clinical trials | 60 | 60 | 60 |  | 0%
- Develop project | 60 | 8 |  |  | 0%
- Commission project | 68 | 50 |  |  | 0%
- Close project | 118 | 2 |  |  | 0%
Inventorisation of programme benefit Q1 | 5 | 4 | 5 | 4 | 100%
Inventorisation of programme benefit Q2 | 18 | 4 | 18 | 4 | 100%
Inventorisation of programme benefit Q3 | 31 | 4 |  |  | 0%
Inventorisation of programme benefit Q4 | 44 | 4 |  |  | 0%
Inventorisation of programme benefit Q5 | 57 | 4 |  |  | 0%
Inventorisation of programme benefit Q6 | 70 | 4 |  |  | 0%
Inventorisation of programme benefit Q7 | 83 | 4 |  |  | 0%
Inventorisation of programme benefit Q8 | 96 | 4 |  |  | 0%
Inventorisation of programme benefit Q9 | 109 | 4 |  |  | 0%
Inventorisation of programme benefit Q10 | 122 | 4 |  |  | 0%
Inventorisation of programme benefit Q11 | 135 | 4 |  |  | 0%
Inventorisation of programme benefit Q12 | 148 | 4 |  |  | 0%
Progress reporting to programme board Q1 | 11 | 1 | 11 | 1 | 100%
Progress reporting to programme board Q2 | 24 | 1 | 24 | 1 | 100%
Progress reporting to programme board Q3 | 37 | 1 |  |  | 0%
Progress reporting to programme board Q4 | 50 | 1 |  |  | 0%
Progress reporting to programme board Q5 | 63 | 1 |  |  | 0%
Progress reporting to programme board Q6 | 76 | 1 |  |  | 0%
Progress reporting to programme board Q7 | 89 | 1 |  |  | 0%
Progress reporting to programme board Q8 | 102 | 1 |  |  | 0%
Progress reporting to programme board Q9 | 115 | 1 |  |  | 0%
Progress reporting to programme board Q10 | 128 | 1 |  |  | 0%
Progress reporting to programme board Q11 | 141 | 1 |  |  | 0%
Progress reporting to programme board Q12 | 154 | 1 |  |  | 0%
Programme closure | 150 | 10 |  |  | 0%
- Create overview of programme benefits | 150 | 4 |  |  | 0%
- Create final progress report | 154 | 2 |  |  | 0%
- finalise and close files | 150 | 10 |  |  | 0%