## Projectplanner
Projectplanner: Virtual consultation package
[5 empty] | Period | 26 |  |  | Duration plan | [6 empty] | Actual start date | [8 empty] | % complete |  |  |  |  | Actual (outside planning) | [9 empty] | % Complete (outside planning)
Activity | Start of activitiy | Duration | Actual start date | Actual duration | Percentage complete | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65
Project formulation | 25 | 1 | 25 | 1 | 100%
- Benefit identification | 25 | 1 | 25 | 1 | 100%
- Project brief development | 25 | 1 | 25 | 1 | 100%
- Define project management structure | 25 | 1 | 25 | 1 | 100%
- Obtain approval from pgoram manager | 26 | 1 | 26 | 1 | 100%
Project preparation | 27 | 3 | 27 |  | 5%
- Set up team | 27 | 1 | 27 |  | 0%
- Analyse stakeholders | 27 | 1 | 27 |  | 0%
- Elaborate deliverables | 27 | 1 | 27 |  | 0%
- Identify activities | 27 | 2 | 27 |  | 0%
- Make a budget | 28 | 1 |  |  | 0%
- Develop project plan | 28 | 1 |  |  | 0%
- Set up project management instruments and structure | 29 | 1 |  |  | 0%
- Approval from programme manager | 30 | 1 |  |  | 0%
Project implementation | 30 | 28 |  |  | 0%
- Identify potential users | 31 | 1 |  |  | 0%
- Identify demand | 31 | 1 |  |  | 0%
- Identify needs | 31 | 1 |  |  | 4%
- Make functional design | 32 | 2 |  |  | 0%
- Identify potential solution partners | 34 | 2 |  |  | 0%
- Launch procurement process | 36 | 3 |  |  | 0%
- Select solution provider | 39 | 1 |  |  | 0%
- Improve functional design with solution provider | 40 | 2 |  |  | 0%
- Technical implementation | 42 | 4 |  |  | 0%
- Test application | 46 | 1 |  |  | 0%
- Review test results | 47 | 1 |  |  | 0%
- Make technical adjustments | 47 | 2 |  |  | 0%
- Second test application | 49 | 1 |  |  | 0%
- Make techincal adjustments | 50 | 1 |  |  | 0%
- Handover of application to organisation | 51 | 1 |  |  | 0%
- Develop manual for staff | 51 | 1 |  |  | 0%
- Start training of staff | 52 | 3 |  |  | 0%
- Launch use of virtual consultation package | 55 | 1 |  |  | 0%
- Evaluate user experience and uptake | 58 | 1 |  |  | 0%
Project monitoring | 27 | 33 | 27 |  | 5%
- Develop monitoring plan to follow uptake | 27 | 1 | 27 |  | 36%
- Approve monitoring plan | 28 | 1 |  |  | 0%
Progress reporting to programme manager Q1
Progress reporting to programme manager Q2
Progress reporting to programme manager Q3 | 37 | 1 |  |  | 0%
Progress reporting to programme manager Q4 | 50 | 1 |  |  | 0%
Progress reporting to programme manager Q5 | 63 | 1 |  |  | 0%
Progress reporting to programme manager Q6 |  |  |  |  | 0%
Progress reporting to programme manager Q7 |  |  |  |  | 0%
Progress reporting to programme manager Q8 |  |  |  |  | 0%
Progress reporting to programme manager Q9 |  |  |  |  | 0%
Progress reporting to programme manager Q10 |  |  |  |  | 0%
Progress reporting to programme manager Q11 |  |  |  |  | 0%
Progress reporting to programme manager Q12 |  |  |  |  | 0%
project closure | 59 | 4 |  |  | 0%
- Create overview of programme benefits and project deliverables | 59 | 2 |  |  | 0%
- Create final progress report | 63 | 1 |  |  | 0%
- finalise and close files | 63 | 1 |  |  | 0%